## Timeplan
Category | Task | Hours |  | Sprint 2 | [31 empty] | Finalization
|  |  |  | Week 1 | [8 empty] | Week 2 | [31 empty] | Week 3
|  |  |  | Day 5 | [7 empty] | OOO | Day 6 | [6 empty] | Day 7 | [7 empty] | Day 8 | [7 empty] | Day 9 | [7 empty] | OOO | Day 10
|  | [h]:mm:ss |  | 20/02/2026 | [7 empty] | 21. - 23.02.2026 | 24/02/2026 | [6 empty] | 25/02/2026 | [7 empty] | 26/02/2026 | [7 empty] | 27/02/2026 | [7 empty] | 28. - 02.03.2026 | 2026-03-03
Meetings | Sprint 2 Planning | should | 1:00 | s
|  | Is | 1:00 | i
| Expert meeting: progress check and confirm Sprint 2 runtime integration path | should | 1:00 | [11 empty] | s
|  | Is | 1:00 | [11 empty] | i
Planning + Journaling | Creating Gannt chart for Project for Sprint 2, update Kanban board tickets | should | 2:00 |  | s | s
|  | Is | 2:00 |  | i | i
| Workjournaling | should | 6:00 | [7 empty] | s | [7 empty] | s | [7 empty] | s | [7 empty] | s | [7 empty] | s | [8 empty] | s
|  | Is | 6:00 | [14 empty] | i | i | [7 empty] | i | [7 empty] | i | [7 empty] | i | [8 empty] | i
Research | Confirm model sources: official HF repo + license + artifacts (safetensors vs GGUF) | should | 1:00 |  |  |  | s
|  | Is | 1:00 |  |  |  | i
| Confirm GGUF artifact repo + pick baseline file (Q4_K_M) + download approach | should | 1:00 |  |  |  | s
|  | Is | 1:00 |  |  |  | i
Runtime PoC | PoC run: llama-cli loads GGUF and answers 1 prompt (save log + screenshot) | should | 1:00 |  |  |  |  | s
|  | Is | 1:00 |  |  |  |  | i
Documentation update | Update docs: A02/A03 entries + H01 validation result + evidence links | should | 1:00 | [5 empty] | s
|  | Is | 1:00 | [5 empty] | i
Backend Integration | Implement LlamaCppAdapter skeleton (subprocess call, timeouts, safe capture) | should | 1:00 | [6 empty] | s
|  | Is | 1:00 | [6 empty] | i
| Integrate adapter selection (LLM_BACKEND=llamacpp) + config/env parameters | should | 1:00 | [10 empty] | s
|  | Is | 1:00 | [10 empty] | i
Backend Hardening | Hardening: OpenAI-style error responses + request logging + input validation tweaks | should | 2:00 | [11 empty] | s | s
|  | Is | 2:00 | [11 empty] | i | i
| Hardening: optional /v1/models (minimal) + README run command updates | should | 2:00 | [13 empty] | s | s
|  | Is | 2:00 | [13 empty] | i | i
Testing | Tests: contract tests + negative tests (e.g., stream=true returns OpenAI error) | should | 1:00 | [15 empty] | s
|  | Is | 1:00 | [15 empty] | i
Performance | Perf: run perf script with llamacpp adapter and store JSON evidence | should | 2:00 | [16 empty] | s | s
|  | Is | 2:00 | [16 empty] | i | i
| Perf: update perf-baselines.md with comparison notes (mock vs llamacpp) | should | 1:00 | [18 empty] | s
|  | Is | 1:00 | [18 empty] | i
Frontend baseline | Serve UI at /ui and verify responsive layout (desktop + mobile) | should | 3:00 | [19 empty] | s | s | s
|  | Is | 3:00 | [19 empty] | i | i | i
Frontend UX | Frontend UX: thinking indicator, disable send while pending, error display | should | 2:00 | [22 empty] | s | s
|  | Is | 2:00 | [22 empty] | i | i
End-to-End & Demo | Manual E2E checklist: API + UI + errors + latency header (record notes) | should | 4:00 | [24 empty] | s | s | s | s
|  | Is | 4:00 | [24 empty] | i | i | i | i
| Demo runbook: commands checklist (run, test, perf, open UI) + demo script | should | 2:00 | [28 empty] | s | s
|  | Is | 2:00 | [28 empty] | i | i
Review and Wrap-up Sprint 2 | Sprint Review + Retro notes + backlog refinement | should | 1:00 | [30 empty] | s
|  | Is | 1:00 | [30 empty] | i
Tracking | Update A05 risks/deviations + link commits/evidence; finalize sprint status | should | 1:00 | [31 empty] | s
|  | Is | 1:00 | [31 empty] | i
Documentation Transfer | Transfer Markdown Dokumentation into A4 Doc | should | 14:00 | [32 empty] | s | s | s | s | s | s | s |  |  | s | s | s | s | s | s | s
|  | Is | 14:00 | [32 empty] | i | i | i | i | i | i | i |  |  | i | i | i | i | i | i | i
Total |  | should | 51:00 | 9:00 | [8 empty] | 8:00 | [6 empty] | 9:00 | [7 empty] | 9:00 | [7 empty] | 8:00 | [8 empty] | 8:00
|  | Is | 51:00 | 8:00 | [8 empty] | 9:00 | [6 empty] | 9:00 | [7 empty] | 9:00 | [7 empty] | 8:00 | [8 empty] | 8:00
|  |  |  | s | Should |  |  | i | Is
Legend
OOO | Out of Office
Milestones | Yellow Line
Time blocks represent 1-hour planning units. Minor deviations (±30 min) are documented in the work journal and absorbed within sprint capacity. Despite block-based tracking, the effective working time corresponds to the required 8 hours per day.

## Variables
Start | 13/2/2026
Schooldays | 16/2/2026 | 23/2/2026 | 2026-02-03
End | 2026-03-03