## Timeplan
Category | Task | Hours |  | Sprint 1
|  |  |  | Week 1 | [8 empty] | Week 2
|  |  |  | Day 1 | [7 empty] | OOO | Day 2 | [7 empty] | Day 3 | [7 empty] | Day 4
|  | [h]:mm:ss |  | 13/02/2026 | [7 empty] | 14. - 16.02.2026 | 17/02/2026 | [7 empty] | 18/02/2026 | [7 empty] | 19/02/2026
Meetings | Sprint Planning | should | 1:00 | s
|  | Is | 1:00 | i
| Expert meeting (kickoff, constraints, acceptance) | should | 1:00 |  | s
|  | Is | 1:00 |  | i
Journaling | Creating Gannt chart for Project | should | 1:00 |  |  | s
|  | Is | 1:00 |  |  | i
| Workjournaling | should | 0:00 | [7 empty] | s | [8 empty] | s | [7 empty] | s | [7 empty] | s
|  | Is | 2:00 | [7 empty] | i | [8 empty] | i
Analysis | A01 Scope + success criteria v0.1 (in/out) | should | 1:00 |  |  |  | s
|  | Is | 1:00 |  |  |  | i
| A04 Architecture draft v0.1 (backend, adapters, flows) | should | 1:00 |  |  |  |  | s
|  | Is | 1:00 |  |  |  |  | i
Project Setup | Repo setup (README, gitflow branches, .gitignore) | should | 1:00 | [5 empty] | s
|  | Is | 1:00 | [5 empty] | i
Backend Baseline | Backend scaffold (FastAPI, config, logging) | should | 2:00 | [6 empty] | s | s
|  | Is | 2:00 | [6 empty] | i | i
Research and Decisions | A02/A03 Research log start (Apertus, runtimes, OpenAI API scope) | should | 2:00 | [9 empty] | s | s
|  | Is | 2:00 | [9 empty] | i | i
| H01 Runtime decision record v0.1 (llama.cpp vs alternatives) | should | 1:00 | [11 empty] | s
|  | Is | 1:00 | [11 empty] | i
Backend API | POST /v1/chat/completions (OpenAI-style response shape, mock) | should | 2:00 | [12 empty] | s | s
|  | Is | 2:00 | [12 empty] | i | i
| Adapter interface + factory wiring (mock adapter integrated) | should | 2:00 | [14 empty] | s | s
|  | Is | 2:00 | [14 empty] | i | i
Quality and Docs | A12 DoD + test concept skeleton v0.1 + local commands | should | 1:00 | [16 empty] | s
|  | Is | 1:00 | [16 empty] | i
Backend Hardening | Request/response validation + consistent error handling | should | 2:00 | [17 empty] | s | s
|  | Is | 0:00
| Mock adapter behaviour: parameters (model/temp/max_tokens) | should | 2:00 | [19 empty] | s | s
|  | Is | 0:00
Testing | Pytest contract tests: /health + /v1/chat/completions | should | 2:00 | [21 empty] | s | s
|  | Is | 0:00
Performance (H08) | Perf script baseline (make perf) + save JSON results | should | 2:00 | [23 empty] | s | s
|  | Is | 0:00
Frontend Baseline | Responsive chat UI (basic LLM interaction features) | should | 4:00 | [25 empty] | s | s | s | s
|  | Is | 0:00
| UX latency handling: thinking indicator + error states | should | 2:00 | [29 empty] | s | s
|  | Is | 0:00
Review and Wrap-up Sprint 1 | Sprint Review + Retro notes + backlog refinement | should | 1:00 | [31 empty] | s
|  | Is | 0:00
Tracking | A05 Risk log v0.1 + decision log updates | should | 1:00 | [32 empty] | s
|  | Is | 0:00
Total |  | should | 32:00 | 9:00 | [8 empty] | 9:00 | [7 empty] | 9:00 | [7 empty] | 9:00
|  | Is | 18:00 | 9:00 | [8 empty] | 9:00 | [7 empty] | 0:00 | [7 empty] | 0:00
|  |  |  | s | Should |  |  | i | Is
Legend
OOO | Out of Office
Milestones | Yellow Line
Time blocks represent 1-hour planning units. Minor deviations (±30 min) are documented in the work journal and absorbed within sprint capacity. Despite block-based tracking, the effective working time corresponds to the required 8 hours per day.

## Variables
Start | 13/2/2026
Schooldays | 16/2/2026 | 23/2/2026 | 2026-02-03